## BOM Material Tracker
Material Name | Qty | Unit | BOM Created Date | PR Created Date | PR Approved Date | PO Created Date | PO Approved Date | Target Receipt Date | Actual Receipt Date | Notes / Vendor
PLC CPU Module - Siemens S7-1500 | 1 | Nos | 2026-05-01 | 2026-05-03 | 2026-05-06 | 2026-05-08 | 2026-05-12 | 2026-06-10 |  | Critical item, single vendor
HMI Panel 10-inch Touchscreen | 1 | Nos | 2026-05-01 | 2026-05-04 | 2026-05-07 | 2026-05-09 | 2026-05-13 | 2026-06-15 |  | Confirm resolution with design
Servo Drive - 2kW AC Servo | 4 | Nos | 2026-05-02 | 2026-05-05 | 2026-05-09 | 2026-05-11 | 2026-05-15 | 2026-06-20 |  | Long lead item — order early
Servo Motor - 2kW | 4 | Nos | 2026-05-02 | 2026-05-05 | 2026-05-09 | 2026-05-11 | 2026-05-15 | 2026-06-20 |  | Pair with servo drive above
Safety Relay - Pilz PNOZ | 2 | Nos | 2026-05-03 | 2026-05-06 | 2026-05-10 |  |  | 2026-06-05 |  | PR pending approval
E-Stop Mushroom Button - Red | 3 | Nos | 2026-05-03 |  |  |  |  | 2026-05-30 |  | PR not yet created
Tower Lamp - 3 Layer LED | 2 | Nos | 2026-05-04 | 2026-05-07 | 2026-05-11 | 2026-05-13 | 2026-05-17 | 2026-06-25
Power Supply 24V DC 10A | 2 | Nos | 2026-05-04 | 2026-05-08 | 2026-05-12 | 2026-05-14 | 2026-05-18 | 2026-06-12 | 2026-06-10 | Received ahead of schedule
Control Cable - 1.5sqmm 4 Core | 200 | Mtr | 2026-05-05 | 2026-05-08 | 2026-05-12 | 2026-05-14 | 2026-05-18 | 2026-06-08 | 2026-06-08 | Received on time
Terminal Block - 2.5sqmm | 50 | Nos | 2026-05-05 | 2026-05-09 | 2026-05-13 | 2026-05-15 | 2026-05-19 | 2026-06-05 |  | Vendor: Phoenix Contact
VFD - 5HP 3 Phase | 1 | Nos | 2026-05-06 |  |  |  |  | 2026-07-01 |  | BOM finalized, awaiting PR
Encoder - Incremental 1000PPR | 4 | Nos | 2026-05-06 | 2026-05-10 | 2026-05-14 | 2026-05-16 | 2026-05-20 | 2026-06-22

## Instructions
How to use this sheet with the Material Procurement Tracker
1. Fill in one row per material — keep the column headers unchanged.
2. Dates must be in YYYY-MM-DD format (e.g. 2026-06-15).
3. Leave a date cell blank if that stage hasn't happened yet.
4. Leave 'Actual Receipt Date' blank until the material is physically received.
Reminder of automatic alert rules in the tracker app:
- PR Created turns red if not filled within 3 days of BOM Created date.
- PO Created turns red if not filled within 3 days of PR Approved date.
- Target Receipt turns red once the date passes without an Actual Receipt date.
5. Upload this file to your BOM storage location (e.g. GitHub repo, SharePoint, network drive).
6. Paste the link/path into the 'BOM Location' field on the tracker page.
7. Manually re-enter each material and its dates into the tracker UI
(the tracker does not auto-import this Excel file — it is a planning/reference sheet).